## Template
PM Essentials
Project Transition
Template
Aug. 31, 2021
Template Description
Purpose
The Project Transition template is a collection of checklists to help the project manager and project team identify the transition tasks that need to be completed for the go-live event.
How to Use
Complete or replace the fields with information specific to your project transition. Many of the items listed in the templates are meant to be suggestive rather than prescriptive. Feel free to expand or contract the checklists as needed.
Best Practice
Transition planning usually begins when testing and validation is underway as the components to be deployed are coming into focus, and the functionality and tools that are going live are seen in their actuality, thereby clarifying the stakeholder impact.
Notes on Templates
Go live plan template - this is an integration checklist that combines the sub-plans listed below: Cutover, Hypercare/Command Center, Knowledge Transfer, Rollback, and Resource list.
Cutover plan template - this is the technical go-live checklist, also called a release plan.
Hypercare / Command Center plan template - this checklist identifies the elements needed for post-deployment monitoring
Rollback plan template - this checklist provides the means to for the team to restore the legacy solution in the event that the deployment fails.
Knowledge Transfer template - this listing identifies the new process that will be in place once the new solution goes live. All impacted stakeholders should be identified and be apprised of the changes set forth in the Knowledge Transfer document.
Resource list template - Provide a list of all project team members (and their backups) involved with the planning and execution of transition.
Note: The PM Essentials Transition Planning Template is customizable as you see fit, on a per project basis, meeting specific needs of the project and/ or your organization’s policies. The provided sections are suggestions but can be tailored as applicable.
**NOTE: Please remove this page when using this template.**
PM Essentials Project Transition template by the Texas Department of Information Resources

## Go Live plan
# | Task | Dependency | Due Date | Owner | Others involved | Status
1 | Pre-Go Live (readiness pre-conditions)
2 | Testing
3 | Network testing complete
4 | User testing complete
5 | Security testing complete
6 | Load testing complete
7 | Stage environment testing complete
Service catalog updated
8 | Planning
9 | Cutover plan complete
10 | Network switchover mapping plan complete
11 | Code and configuration mapping and migration plan complete
12 | Rollback plan complete
13 | Go Live testing plan complete
14 | Hypercare / Command Center plan complete with exit criteria (for larger projects)
Knowledge transfer to Helpdesk and operations complete
16 | Resource List completed
17 | Sign off
18 | Go-NoGo decision ready for sign off or already signed off
19
20 | Communications
21 | Communication to executive leadership
22 | Communication to department managers and staff
23 | Communication and training to end users and customers
24 | Communication and training to helpdesk and support staff
25 | Communication to other agencies and vendors
26 | [add rows as needed]
27 | Go Live
28 | Execute cutover plan
29 | Declare the new system live
30 | Execute Hypercare / Command Center plan
31 | [add rows as needed]
32 | Post-Go Live
33 | System and Network administration
34 | Take new baseline performance; analyze with original
35 | Continue to monitor system and network performance
36 | Hypercare / Command Center
37 | Continue to execute Hypercare / Command Center plan
38 | Monitor for high severity tickets
39 | Transition to Operations
40 | Prepare to execute exit portion of Hypercare / Command Center plan
41 | Assume normal operation
42 | [add rows as needed]

## Cutover plan
# | Task | Dependency | Owner | Others involved | Status
Pre-Go Live (readiness pre-conditions)
Resource list completed (see right)
Cutover plan reviewed and finalized with team
[add rows as needed]
Go Live
Go Live planned start date and time: mm/dd/yyyy at hh:mm
Code and configuration migration
Stage Server 1 to Production Server 1
Stage Server 2 to Production Server 2
Stage Server 3 to Production Server 3
Stage Server 4 to Production Server 4
Data migration
Stage Database 1 to Production Database 1
Stage Database 2 to Production Database 2
Validation
Smoke check Production Servers 1-4
Functionality check (including regression testing) for Production Server 1
Functionality check (including regression testing) for Production Server 2
Functionality check (including regression testing) for Production Server 3
Functionality check (including regression testing) for Production Server 4
Network configuration and security
DNS1 and VLAN1 mapping
DNS2 and VLAN2 mapping
Stage Server 1 to Production Server 1
Stage Server 2 to Production Server 2
Stage Server 3 to Production Server 3
Stage Server 4 to Production Server 4
Firewall rules for Production Server 1
Firewall rules for Production Server 2
Firewall rules for Production Server 3
Firewall rules for Production Server 4
Smoke check Production Server 1-4
Functionality check for Production Server 1
Functionality check for Production Server 2
Functionality check for Production Server 3
Functionality check for Production Server 4
Go Live complete
[add rows as needed]
Post-Go Live
System and Network administration
Take new baseline performance; analyze with original
Continue to monitor system and network performance
Hypercare / Command Center
Continue to execute Hypercare / Command Center plan
Monitor for high severity tickets
Transition to Operations
Prepare to execute exit portion of Hypercare / Command Center plan
Assume normal operation
[add rows as needed]

## Hypercare-CommCenter plan
# | Task | Dependency | Owner | Others involved | Status
Pre-Go Live (readiness pre-conditions)
Confirm resource list with email and phone numbers
Staffing schedule identified
Coordination with HelpDesk and operations established
Facility / conference room reserved
Entry criteria identified
Exit critera identified
Hypercare/Command Center plan reviewed and finalized with team
[add rows as needed]
Go Live
Daily standups (time, location, venue)
Daily status reporting (frequency, audience)
Hypercare / Command Center team resolves issues
Monitor for meeting the exit criteria
Post-Go Live
Exercise exit plan; transition to operations
Hypercare / Command Center complete
[add rows as needed]

## Knowledge Transfer
# | Knowledge to be Transferred | Dependency | Primary stakeholder | Department | Others stakeholders
1 | [Name of Process 1]
2 | step 1 of process
3 | step 2 of process
4 | step 3 of process
5 | step 4 of process
6 | step 5 of process
7 | step 6 of process
8 | step 7 of process
9 | step 8 of process
10 | [Name of Process 2]
11 | step 1 of process
12 | step 2 of process
13 | step 3 of process
14 | step 4 of process
15 | step 5 of process
16 | step 6 of process
17 | step 7 of process
18 | step 8 of process
19 | [add rows as needed]

## Rollback plan
# | Task | Dependency | Owner | Others involved | Status
Pre-Go Live (readiness pre-conditions)
Confirm resource list with email and phone numbers
Rollback plan reviewed and finalized with team
[add rows as needed]
Go Live
Rollback criteria
Features which must be functional
Connectivity which must be operational
[name of person] to authorize rollback
If rollback decision = Yes, then
Reverse execute the relevant parts of the cutover plan
Code and configuration migration
Network changes and redirects
Restore backed up data
Validation
Smoke check Production Server 1-4
Functionality check for Production Server 1
Functionality check for Production Server 2
Functionality check for Production Server 3
Functionality check for Production Server 4
Rollback complete
[add rows as needed]
Post-Go Live
System and Network administration
Continue to monitor system and network performance
Execute Communication plans regarding Rollback
Assume normal operation
[add rows as needed]

## Resource List
Team member / Resource | Organization | Role | Email | Phone
Cutover Lead
Cutover Lead (backup)
Code and Configuration Migration Lead
Code and Configuration Migration Lead (backup)
Data Migration Lead
Data Migration Lead (backup)
Network configuration Lead
Network configuration Lead (backup)
Hypercare/Command Center Lead
Hypercare/Command Center Lead (backup)
Storage/Backup SME
Storage/Backup SME (backup)
Network SME
Network SME (backup)
Firewall and Security SME
Firewall and Security SME (backup)
Communication Lead
Project Manager
Technical Lead
Technical Architect
HelpDesk Lead
Product Owner
Project Owner
[add rows as needed]
Conference Bridge # | nnn-nnn-nnnn
Email Distribution group | [mailbox name]
Teams project group | [URL]

## dropdown (hidden)
Status
Not started
In progress
Completed
On hold