## Instructions
Risk Register Instructions
A risk register for all types of projects is provided in the Risk Register worksheet. The risk register is organized with the following columns:
Risk Statement: a clear and concise explanation of the context of the risk. The risk statement includes the:
Risk (Event) Description: explanation of the risk event or the occurrence that has caused the risk (e.g., customer submits changes to requirements after requirements are baselined)
Risk Consequence: potential effect or outcome of the risk (e.g., changes could extend project delivery completion date)
Risk Trigger/Causes: act or event that serves as a stimulus and initiates or precipitates the risk
Assessment: a value (e.g., Low=1, Medium=2, High=3) that represents the result of identifying, classifying, analyzing, and prioritizing risk
Impact: result of determining the nature of possible effects of the risk
Probability: degree of likelihood or chance that the risk will occur
Level of Control: extent to which the project team lacks control over the risk being realized
Total: sum of the Impact, Probability, and Level of Control values; the cell contains a formula that will calculate the sum automatically
Risk Response Strategy: one or more options to address the risk
Actions Required to Implement Response Strategy: activities that will be carried out in order to accomplish the risk response strategy (e.g., revising the Project Plan to include additional activities, defining various alternatives to address the risk)
Risk Owner: name of the individual(s) or party(s) responsible for managing the risk
Completion Date: date mm/dd/yy the risk response actions were completed

## Risk Register
Risk Register
Risk Register
Agency/Organization Name | [9 empty] | Version Number
Project Name | [9 empty] | Revision Date mm/dd/yy
| RISK STATEMENT |  |  | ASSESSMENT (Low=1, Medium=2, High=3)
Risk # | Risk (Event) Description | Impact (Consequence) Description | Risk Trigger / Causes | Impact | Probability | Level of Control | Total | Risk Response Strategy | Actions Required To Implement Response Strategy | Risk Owner | Completion Date mm/dd/yy
1 | [6 empty] | 0
2 | [6 empty] | 0
3 | [6 empty] | 0
4 | [6 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16 | [6 empty] | 0
17 | [6 empty] | 0
18 | [6 empty] | 0
19 | [6 empty] | 0
20 | [6 empty] | 0